## Sheet1
APPENDIX C – Ci3 India - ACTION ITEM 1 - Identification and Formulation of KPIs - Interim Output for Roundtables in Oct. 2016
KPIs TEMPLATE & SHORTLISTED KPIs – 31 Aug. 2016 - Drafted by Dr Gangadhar Mahesh with Prof. Mohan Kumaraswamy & SHORTLISTED with ACTION TEAM 1 inputs
FEEDBACK INVITED (in Column H + even still in Columns D,E,F) to SHORTLIST DESIRED (valuable–beneficial + viable-practical) KPIs for Indian Construction Industry
Items in Red & Italics still need Suggestions
Items in Shaded Cells need Revisitng with Proposer
[A] PERFORMANCE DIMENSION | [B] PERFORMANCE CRITERION - to be measured | [C] KPIs - KEY PERFORMANCE INDICATORS - with which to measure | [D] - (A) Is KPI Useful? Y/N (B) Is Data available to derive KPI? Y/N | [E] - If ‘Y’ to (A) and (B) - Agree present format? / Suggest Improvements: | [F] - If ‘N’ to (A) and/or (B) - Brief reasons: | [G] - WIs – WEIGHTING INDICATORS– with which to weight a KPI value | [H] - TYPICAL ‘VALUE RANGES’ of the KPIs (under average conditions)
DESIGN PHASE (NOTE –You may also suggest any Additions even now if Important, apart from commenting on those below)
Client Effectiveness | Clarity & Completeness of Site Due diligence | Number of key points checked and closed before start of project with reference to a standard brief
| Clarity & Completeness of project brief | No. of RFI's after initial brief / Project Value
| Certainty of project brief | Number of change orders due to client revisions
No. of Additions or Alterations after Initial Brief / Project value
Value of Additions or Alterations after Initial Brief / Project value
| Procurement planning efficiency and integration | Number of consultants on-board before master plan/ No. of consultants on-board after master plan
No. of consultants engaged pre-contract stage / No. of consultants engaged post-contract stage
No. of specialist subcontractors engaged pre-contract stage / No. of specialist contractors engaged post-contract stage
| End User identification OR End User Needs identification? | (i) Commercial buildings - Floor space clearly demarcated to end-users (types) / Floor space not earmarked to an end-user (type);
(ii) Residential buildings - As built FAR / Originally designed FAR, As built units / Originally designed no. of units -TOO VAGUE?
Client Efficiency | Response to Consultant + …. | RFI (Request for Information) turnaround TIME – for RFIs needing Client Inputs/ Sign-off + ……
Consultant Performance (during Design Phase) | Design efficiency | Consultant Fee / Total Project value
Design time / Total project time
Project Value/ No. of drawings ? Suggest to REPLACE DENOMINATOR with 'No. of REVISED drawings needed ONLY to clarify'
Time to Submit for Statutory Approval/ project time
Average response time to Effect Essential Changes
No. of RFI's originating from design omissions and errors
Number of changes in DBR based on client/other consultant comments
Attrition rate of Key consultant personnel (Mid-project changes)
% of absenteeism in Design Review Meetings.
| Attention to Lifecycle costs | Relevant Sustainability Indicators …. Many systems available-Must choose! Agreed to limit (here) to environmental
| Design Management | Time for outline design / overall design time available
Time for detailed design / overall design time available
Time taken to appoint other consultants / total preconstruction time
| Peer Review | Peer Review rating on structural (& separately MEP) design
| Peer to Peer Communication | Peer to peer communication and turnaround time
Cost reduction from third party audit based redesign / total project cost (reductions in steel, concrete; improvements in constructability ...)
End-User and Input and Early Contractor Involvement | Value Engineering | Value gained / Project cost as a %
Cost Saved / Project cost as a %
Time saved on planning / resource mobilization on early contractor involvement as a %
| Constructability checks | Clash avoidance/detections for various components - Value gained by early avoidance/detection of clashes / Project Cost as a %
Cost saved by design constructability issues raised during meetings before the start of construction. / Project Cost as a %
Statutory Approvals -process & protocols | Speed | Time for each approval (specify approval type)/ total project time
Total time for all approvals / total project time
| Complexity | No. of approvals needed
No. of mandatory contact organisations/ points
No. of layers/ levels to pass through for each approval
Number of unethical incidents noted at government offices during approval (OR overall rating for ease of working)
| Certainty / Consistency | No. of Repeat Submissions (IF /AFTER original submission met specified conditions)
No. of Additional Requirements imposed
Number of unfavorable / difficult or impractical conditions imposed in approvals
Number of RELEVANT changes in Government approval policies from date of Design Brief till date of final approval.
Number of RELEVANT changes in Government approval policies from date of Submssion to date of final approval.
CONSTRUCTION PHASE (You may also suggest any Additions even now if Important, apart from commenting on those below)
Contractor (overall performance) | Reliability | Actual cost / Contract value (as a %)
Delay period / contract duration (as a %)
Actual spent on Over Head vs. Budgeted (as a %) - IRRELEVANT & DIFFICULT TO QUANTIFY?
Special/ Crtitical Action items acted upon within time / Special/ Critical Action items (as a %)
Ethical values - No. of incidents observed and reported.
Site logistics + changes vs initial/ optimal plan (having an impact on time/wastage/cost etc).
| Quality | % cost incurred (or value of works rectified) during DL (Defects Liability) Period / Total Project cost
Quality assessment scores (something like HK PASS or S'pore CONQUAS???)
| EHS | No. of accidents / million man-hours
No. of fatalities / million man-hours
No. of reported incidents of safety infringements/ project duration
Adequacy of drinking water and sanitation facilities on site
Provision of adequate restrooms (% on site /sourced outside)
Adequacy (of facilities etc) of Labor camp and its maintenance
Overall rating by staff
| Human resources | Employee turnover rate (+ Add ONE mor eon 'Overall rating by staff')
| Financial resources | % of delayed payments to suppliers and subcontractors
| Equipment resources | % of delay time due to non-availability of equipment
| Stock-keeping | Average Inventory Value/ Cost / Total Project cost
| Innovativeness | Number of Innovations initiated or attempted on site
Number of high recognitions / awards received by contractor for successful innovations in general
Acceptability of new ideas OR Success of new innovations on site
| Responsiveness | Average Time to respond to specific events (avg. no. of days to reply to communication)
Average No. of iterations to resolve an issue
Productivity
Manpower Productivity = value of work done / total manpower cost
Equipment Usage Productivity = total hours of equipment in use / total hours of equipment at site
% Idling time of each resource – manpower, equipment etc. …(RESTRICT TO MANPOWER, as we have EQUIPMENT above)
Equipment Productivity
Space Productivity
| Claims Consciousness | No. of claims rejected / total no. of claims
value of claims rejected / total value of claims
| Sustainability considetations | G3 indicators
| Mechanization | % of mechanization by work volume
Equipment Skill index = Equipment Training Hours / Total Man Hours NEED a parallel KPI to know level of trained manpowe recruited
| Training | Cost incurred in training imparted to key skilled workers / contract value - NEED a parallel KPI to know level of trained manpowe recruited
| Rework | Cost of rework / contract value as a %
Avoidance of rework - % decrease in Rework - project on project - as measured against an agreed rework estimation mechanism based on past data classified by project type, size etc
| Statutory compliance | Costs attributed to compliance issues / contract value
No. of compliance issues over the course of the project
No. of days delays and costs attributed to compliance issues / contract duration
Client (effectiveness; efficiency; …. ) | Right Decisions | Rework cost attributable to indecsions or client wrong decisions / contract value
Delays attributable to client indecsions or client wrong decisions / contrct period
Overall ease of working arrangements – rate on scale 1 to 10 as rated by other stakeholders
| Quick Decisions | Extra costs (incldg. for Disruptions, Delays + Rework) attributable to delayed or wrong decisions / contract value
Delays attributable to delayed or wrong decisions / contract duration
| Prompt Payments | Average No. of days to Payment after certificate/ No. of Days specified for Payment after certificate
| Budget | No. of change orders / contract value
change order value / contract value
Change order linked delays / contract duration
| Traceability of decisions | No. of orally issued change orders / No. of documented orders
Consultant (overall performance) | Delegation Matrix | Percentage of bills released at project level vs total contract value.
Amount cleared by site vs total contract value
Total number of Change requests processed at site vs total number of requests
| Environment for Innovation, Ideas and Soft Skill development | No. of motivational events for safety, productivity, sustainability initiatives, ideas & innovations.
| Project Completion & Closure | Planned duration of contract vs actual time for physical completion (start of DLP)
"Closure of Contractors Payments" as a % = time taken from physical completion to commercial closure of contracts (final bill payment)/ Total project contract duration
| Consultant Efficiency | No. of serious errors and omissions
No. of days delays due to errors and omissions / contract duration
Cost escalation due to errors and omissions / contract value
| Response to Client needs | Average Time to required action
Number of project review meetings attended / Total No. of project review meetings
| Response to Contractor & other supply chain issues | Average RFI turnaround time – to required Solution
| Reliability | Rework Value attributable to Consultant /contract Value
Delays attributable to Consultant / contract duration
| Proactiveness in anticipating and minimizing (a) contractual issues ; (b) construction issues | No. of risks identified and mitigated
Cost of mitigating risks identified / forecast cost of consequences
Forecast impact of change orders / actual impact
| Integration | Peer to peer communication and turnaround time
| Project Closeout | No. of days to closeout from practical completion date /contract project duration (as a %)
Closeout documentation quality
Statutory Approvals - Effectiveness and efficiency (during or after co0nstruction) | Speed | Time for each approval (specify approval TYPE) / total project time
Total time for all approvals / total contract duration
| Complexity | No. of approvals needed
No. of mandatory contact organisations/ points
Average No. of layers/ levels to pass through for each approval
| Certainty/ Consistency | No. of Repeat Submissions (IF /AFTER original submission allegedly met specified conditions)
No. of Additional Requirements imposed
| Government Policy Changes | Value of changes required to project due to policy changes / contract value (as a %)
| Provisions for changes and additions, and Clarity in process for approvals | Whether Change incorporation flexibility is available?
No. of approvals needed
No. of mandatory contact organisations/ points
Average No. of layers/ levels to pass through for each approval
Project Procurement Mode incldg., Team Selection, Contract type, Payment modalities etc. + …. | Proactive in boosting performance in: Time, Cost, Quality / Reliability ...+ ... | No. of tender queries
Time given to contractors to bid / Total Project time as a % + ADD NEW ONE: Average Tendering Cost/ Contract Value (as a %)
Tender evaluation time / project duration
Tender evaluation cost / contract value
No. of disputes
Disputed value / contract value
Subcontracted contract value total contract value
Number of nominated/named subcontractors
Nominated/named subcontract value to total contract value
Vendor selection /approval - Average turnaround time
Contractor’s feedback rating
Vendor feedback rating
Response time in Procurement Emergencies
No of new products / technologies utilised
No of contractor, consultant and vendor termination incidents
Effectiveness of End-User |  | No. of days delays (Or Time savings) due to end-user requested design changes / contract duration
Cost overrun (Or Cost Savings) due to end-user requested design change / contract value
BUSINESS OUTCOMES (NOTE - You may also suggest any Additions even now if Important, apart from commenting on those below)
Brand Building | Brand credibility and end-user satisfaction | User evaluation scores
Customer feedback survey scores.
Repeat business turnover / Total turnover
Credibility/ confidence
Pending disputes to total no of disputes in a financial year
Turnover/ No. of major disputes
No. of major disputes / No. of End-Users
Variation in market share
Turnover by reference to total turnover
Corporate Social responsibility scores
Number of deviations from actual sale deed /brochure with actual product given to customer
Project Performance (for each project) | Time performance – certainty (meeting budget); level (against benchmarks); Cost performance ….etc. | Budget variation as a %
Time variation as a %
No. of major specification changes
Value of work affected by specification changes as a % of total contract value
Number of project review meetings conducted per month (avg)
Number of repeat NCs / total number of NCs
Average Retrieval time for documents and records
Number of Complaints from adjacent property owners / government authorities
Noise levels and dust levels during construction compared to average/ allowabe levels
Water consumption cost v/ total construction value
Energy cost (including DG) v/s total construction value
Staff Over Time manhours vs. total staff manhours
Number of unethical issues observed or reported/ year
Contractor’s rating of the projects team
| Compliance | No. of statutory Compliance issues
Safe manhours
| Sustainability (Environmental) | Value spent on Environmental friendly initiatives/ total contract value
Life cycle of installed MEP equipment – Gains (on agreed scales) in Operatabilty/ Maintainability Sustainability/ …?
| Customer complaints | No. of complaints
Repeat complaints of similar nature / Total no of complaints as a %
Meeting Delivery commitment to end-user
Investment Performance (overall) | Financial outcomes | IRR
Cumulative Sq Ft of sales / total inventory
Average inventory turnaround time
Breakeven point of project - CLARIFY
Note on C8: Gangadhar: Key Points in a standard brief to be defined
Note on C9: Gangadhar: Project Value to be defined - Overall project procurement value spent by client
Note on C13: Gangadhar: The term Master P{lan to be defined to indicate a certain stage
Note on C59: Gangadhar: Some sort of quality assessment may be sufficient
Note on C74: Gangadhar: Acceptability criteria to be defined
Note on C167: Gangadhar: Definition of dicpute
Note on C168: Gangadhar: Definition of major dispute